## Project Overview
CredVault Project Overview
Project Name | CredVault
Status | In Progress
Project Type | Web Application - Credential Vault Management System
Priority | Medium
Expected Start Date | 2026-10-11
Expected Completion Date | 2026-11-15
Project Description
CredVault is a Django-based credential vault management system designed for secure storage and retrieval of URLs, emails, usernames, passwords, and IP addresses. The system enforces strict data validation, prevents duplicates through SHA-256 fingerprinting, and provides high-performance bulk import capabilities with PostgreSQL backend. Key features include durable import lifecycle with checkpointing and recovery, sub-second indexed search, administrator authentication, and comprehensive audit trails.

## Task Tracker
Subject / Task | Project | Type | Part of Group | Status | Priority | Main Task (Parent) | Expected Start Date | Expected Completion Date | Details and Task Description
DATA ARCHITECTURE | CredVault | Category | No | Completed | High | - | 2026-10-11 | 2026-10-11 | Foundation layer establishing the core data model for CredVault. Transforms the original flat Record structure into a normalized, deduplicated reference architecture with five independent value tables (Url, Email, User, Pass, Ip) linked through a central Account table. This architecture enables case-insensitive uniqueness enforcement, efficient storage through deduplication, and flexible querying. The design supports millions of records while maintaining data integrity through functional indexes and SHA-256 fingerprinting at the database level.
Schema Normalization & Reference Tables | CredVault | Development | Yes | Completed | High | Data Architecture | 2026-10-11 | 2026-10-11 | Replaced the monolithic flat Record model with five normalized, deduplicated reference tables: Url, Email, User, Pass, and Ip. Each reference table contains only three fields: name (the actual value), created_at, and updated_at timestamps. Critical implementation detail: each table has a functional B-tree index on LOWER(name) to enforce case-insensitive uniqueness at the database level. This means 'Person@Example.COM' and 'person@example.com' cannot both exist - the unique constraint rejects the second insert. The Account table serves as the junction, holding foreign keys to all five reference tables plus a unique fingerprint hash. This normalization reduces storage by eliminating duplicate values (e.g., the same URL appearing in 10,000 records is stored once in vault_url and referenced 10,000 times). Migration 0001 establishes this schema with proper foreign key constraints and cascading behaviors.
SHA-256 Fingerprint Implementation | CredVault | Development | Yes | Completed | High | Data Architecture | 2026-10-11 | 2026-10-11 | Implemented cryptographic duplicate prevention at the Account level using SHA-256 fingerprinting. The fingerprint is computed from the six-tuple (url_id, user_value, email_id, pass_id, ip_id, created_at) where user_value is the literal username string (not a foreign key, since usernames are case-sensitive and stored directly). This hash is stored in Account.fingerprint with a UNIQUE constraint, making it impossible to insert the same credential combination twice regardless of the code path used (ORM, bulk_create, raw SQL, or import). Migration 0002 handles the critical data migration: canonicalizes existing rows to their normalized forms, identifies records that become duplicates after normalization (e.g., three email addresses that all normalize to person@example.com), merges them intelligently by keeping the oldest record and updating references, then backfills fingerprints for all surviving records. The migration includes verification that every stored fingerprint matches what the live model computes, ensuring data integrity. This three-layer defense (canonical normalization → unique reference names → unique account fingerprint) makes duplicates mathematically impossible.
DATA VALIDATION & INTEGRITY | CredVault | Category | No | Completed | High | - | 2026-10-11 | 2026-10-11 | Comprehensive validation layer enforcinging strict format rules for all five credential types. Before this implementation, the system accepted malformed data: 'not a url' was stored as a URL, 'b@@ad' was classified as email, '999.999.1.1' was accepted as an IP address, and 'HTTPS://EXAMPLE.COM/Login' was parsed incorrectly with extract_domain() returning 'https' instead of the domain. The validation module ensures that invalid data is rejected at every entry point (web forms, imports, admin interface, API) with clear error messages, while valid data is normalized to canonical form before storage to prevent semantic duplicates.
Value Format Enforcement Module | CredVault | Development | Yes | Completed | High | Data Validation & Integrity | 2026-10-11 | 2026-10-11 | Created vault/validators.py as the single source of truth for all format validation across the entire application. This module owns five complete validator suites, one for each credential type, each providing three functions: is_valid_* (boolean check), normalize_* (returns canonical spelling or None), and validate_* (raises ValidationError with specific reason). URL validation: optional http:// or https:// scheme (defaults to https if missing), host must be valid labels plus alphabetic TLD of 2+ characters (or IP literal or localhost), port 1-65535 with scheme's default port (80/443) dropped, %xx escapes upper-cased, IDN hosts stored as punycode, trailing slash removed from bare origins. Example: 'HTTPS://Example.COM:443/Login' normalizes to 'https://example.com/Login'. Email validation: RFC-compliant local part (1-64 chars, dots between atoms only, no consecutive dots), domain with valid TLD or [IP] literal, exactly one @, total length ≤254 chars, stored fully lower-cased. Username validation: letters from any Unicode script, digits and . _ - + allowed, single spaces allowed inside (not at edges), must start and end with alphanumeric, @ forbidden (prevents confusion with email), case preserved (usernames are case-sensitive). Password validation: any printable text, 1-500 characters, leading/trailing whitespace trimmed, control characters rejected, case preserved. IP validation: uses Python's ipaddress module for strict validation - octets 0-255 with NO leading zeros (010.0.0.1 rejected), canonical compressed form for IPv6, special values N/A, -, null, none, nil, unknown treated as 'no address' rather than stored as fake values. Every entry point (Add/Edit Record form, reference pages, file/folder import, Django admin) uses these validators, ensuring consistent behavior.
Line Parser with Field Order Enforcement | CredVault | Development | Yes | Completed | Medium | Data Validation & Integrity | 2026-10-11 | 2026-10-11 | Implemented vault/utils.py parse_line() function that enforces the documented field order: URL → email-or-username → password → optional IP address. The parser is intelligent about separator detection: it tries each separator (¦, tab, ;, :) in order and keeps the first one that produces a completely valid record. This handles the critical edge case where a password contains the separator character - for example, 'https://a.com¦bob¦pa:ss:word¦1.2.3.4' with : as separator would naively split into too many fields, but the parser reads the IP from the end (since IP has a known format) and treats everything between the identifier and IP as the password. The identifier field is classified as email only if it passes email validation; otherwise it's treated as username. Blank lines, # comments, and decorative box characters (│, ─, ┌, ┐, etc.) are ignored. The parser rejects lines rather than storing them half-parsed - if any field fails validation, the entire line is skipped and counted as failed. This prevents the old bug where 'not a url¦bob¦secret¦1.2.3.4' would store 'not a url' as a URL. The parser is used by both the web import interface and the importfolder management command, ensuring consistent behavior across all import paths.
Duplicate Prevention System | CredVault | Development | Yes | Completed | High | Data Validation & Integrity | 2026-10-11 | 2026-10-11 | Implemented a three-layer duplicate prevention strategy that makes duplicates mathematically impossible at every level. Layer 1 - Canonical Normalization: Before any lookup or storage, values are normalized to canonical form (URLs lower-cased for scheme/host, emails fully lower-cased, IPs in canonical compressed form). This means 'Person@Example.COM', 'PERSON@EXAMPLE.COM', and 'person@example.com' all become 'person@example.com' before hitting the database. Layer 2 - Unique Reference Names: Each reference table (vault_url, vault_email, vault_user, vault_pass, vault_ip) has a UNIQUE constraint on the name field with a functional index on LOWER(name) for case-insensitive enforcement. Attempting to insert the same normalized value twice raises IntegrityError. Layer 3 - Unique Account Fingerprint: The Account table has a unique fingerprint (SHA-256 hash of the six-tuple) preventing the same credential combination from being stored twice even if individual reference values exist. Import performance was carefully measured: 9,562 rows/s before validation → 9,543 rows/s after, proving that strict validation costs essentially nothing when properly optimized. The hot path was re-optimized to batch lookups and avoid N+1 queries.
AUTHENTICATION & ACCESS CONTROL | CredVault | Category | No | Completed | High | - | 2026-10-11 | 2026-10-11 | Security layer implementing administrator authentication and access control for the credential vault. Ensures that all operations (viewing records, importing data, managing imports, exporting data) require an authenticated administrator session. Uses Django's built-in authentication system with the auth_user table, providing secure password hashing, session management, and protection against common web vulnerabilities (CSRF, session hijacking, etc.).
Administrator Authentication | CredVault | Development | Yes | Completed | High | Authentication & Access Control | 2026-10-11 | 2026-10-11 | Implemented administrator login using Django's authentication framework. All workspace pages and operations now require an authenticated administrator session. Integration includes: Django's auth_user table for storing administrator accounts with PBKDF2 password hashing, authentication middleware that redirects unauthenticated users to the login page, session management with secure cookies, CSRF protection on all forms, and logout functionality. The createsuperuser management command is used to create the initial administrator account. Session data is stored in the database (django_session table) for persistence across server restarts. The authentication system integrates seamlessly with the profile menu UI, which displays the logged-in administrator's username and provides quick access to logout. All import operations, search queries, and data exports are now protected by this authentication layer, ensuring that sensitive credential data is only accessible to authorized administrators.
DATABASE MIGRATION (SQLite to PostgreSQL) | CredVault | Category | No | Completed | High | - | 2026-10-11 | 2026-10-11 | Critical infrastructure migration moving the entire system from SQLite to PostgreSQL 14+ to handle millions of records with sub-second query performance. SQLite's limitations included: no trigram indexes for substring search (14-second searches over 4M records), single-writer locking (blocking concurrent imports), limited COPY performance, and no advanced indexing. PostgreSQL provides: pg_trgm GIN indexes for fast substring search, MVCC for concurrent reads during writes, COPY protocol for high-throughput bulk imports, and advanced indexing strategies. The migration preserves all existing data while enabling the performance characteristics required for production use.
PostgreSQL Migration | CredVault | Development | Yes | Completed | High | Database Migration (SQLite to PostgreSQL) | 2026-10-11 | 2026-10-11 | Complete migration from SQLite to PostgreSQL 14+ with zero data loss. Implemented PostgreSQL-specific optimizations: COPY protocol for high-throughput bulk imports (replacing INSERT statements), connection pooling via psycopg3, and environment-based configuration (POSTGRES_DB, POSTGRES_USER, POSTGRES_PASSWORD, POSTGRES_HOST, POSTGRES_PORT). Created the copy_from_sqlite management command for migrating existing SQLite databases: copies every table in one transaction including administrator accounts, groups, sessions, and admin history while preserving original IDs. The command validates that row counts match and every stored fingerprint is correct before committing - if any check fails, nothing is saved (transaction rollback). Performance improvement: import speed increased from SQLite's ~10,500 records/s (empty DB) to PostgreSQL's ~5,000 records/s with full trigram indexes, but more importantly, substring search dropped from 14 seconds (SQLite, 4M records) to 191ms (PostgreSQL, 1M records) - a 73x improvement. Storage efficiency: 1.5GB for 1M records (PostgreSQL) vs 3.6GB for 4M records (SQLite), roughly 1.5KB per record including all indexes. The migration requires pg_trgm contrib module (included in standard PostgreSQL packages).
Trigram Index Implementation | CredVault | Development | Yes | Completed | Medium | Database Migration (SQLite to PostgreSQL) | 2026-10-11 | 2026-10-11 | Migration 0003 added pg_trgm GIN (Generalized Inverted Index) indexes on all five reference tables (vault_url, vault_email, vault_user, vault_pass, vault_ip) to enable fast substring search. Trigram indexes break text into three-character sequences and index them, allowing PostgreSQL to quickly find rows containing a substring without scanning the entire table. Example: searching for 'corp' in URLs can use 'Bitmap Index Scan on vault_url_name_trgm' to find 'https://vpn.corp.example.net/remote' without reading millions of rows. Performance impact: advanced keyword substring search over 1M records dropped from 1,156ms (SQLite with full table scan) to 191ms (PostgreSQL with trigram index) - a 6x improvement. Advanced URL substring search: 828ms → 181ms. Trade-off: import speed reduced by ~33% (3,670 → 2,440 records/s on 200k test) because each inserted row requires updating the trigram index. This is why the --fast import mode exists: it drops trigram indexes before import and rebuilds them once at the end, recovering the performance. The indexes are critical for the Advanced Search feature which promises 'contains' matching in its UI labels.
IMPORT ENGINE | CredVault | Category | No | Completed | High | - | 2026-10-11 | 2026-10-12 | High-performance bulk import system capable of processing millions of credential records with optimized throughput. The engine reads text files in various formats (pipe, tab, semicolon, or colon-separated), validates each line against strict format rules, deduplicates against existing records, and bulk-inserts new records using PostgreSQL's COPY protocol for maximum throughput. Supports multiple input methods: single file upload, folder upload (webkitdirectory), local/server file paths, and the importfolder management command. Achieves 7,700 records/s on a 2 vCPU sandbox with parallel parse workers and optimized batch sizes. Includes streaming export capabilities for downloading entire filtered datasets in CSV or JSON format.
Bulk File & Folder Import | CredVault | Development | Yes | Completed | High | Import Engine | 2026-10-11 | 2026-10-11 | Implemented high-throughput bulk import in vault/importer.py with multiple input methods. Web UI (/import/ page) supports: (1) single file upload via standard file input, (2) full folder upload using webkitdirectory attribute (recursively reads all files in selected folder), (3) local/server directory paths (one per line in text area) for importing from server filesystem, (4) local/server file paths for specific files. Management command: python manage.py importfolder /path/to/folder1 /path/to/folder2 --ext '*.txt' recursively reads all matching files. The import process: reads every line from every file, parses using the intelligent separator detection, validates each field, normalizes to canonical form, deduplicates against existing records, and bulk-inserts new records in bounded batches (default 250,000 rows). Uses PostgreSQL COPY protocol to stream data into a temporary staging table, then performs set-based INSERT ... ON CONFLICT DO NOTHING ... SELECT to merge into reference tables and Account table. This approach is 10-100x faster than individual INSERT statements. The importer only checks existing Account rows for the batch's URL/password subset rather than scanning the full table, making it scalable to millions of existing records. Blank lines, comments (#), and decorative box characters are ignored. Invalid lines are skipped and counted separately from successful imports.
Streaming CSV/JSON Export | CredVault | Development | Yes | Completed | Medium | Import Engine | 2026-10-11 | 2026-10-11 | Implemented streaming export functionality that exports the entire matching dataset from the database, not just the current paginated page. Uses Django's StreamingHttpResponse with .values_list(...).iterator(chunk_size=2000) to stream data directly from PostgreSQL to the HTTP response without loading everything into memory. This is critical for large exports: a query matching 500,000 records would consume gigabytes of RAM if loaded all at once, but streaming keeps memory usage constant at ~2000 records. Supports two formats: CSV (comma-separated values with proper quoting and escaping) and JSON (array of objects with all fields). The export uses the same filter_accounts() queryset as the search/display pages, ensuring consistency - what you see in search results is exactly what gets exported. The streaming approach allows exports to begin immediately (first bytes sent within milliseconds) rather than waiting for the entire dataset to be prepared. Tested with exports of 150+ records beyond the first page to verify that pagination doesn't limit export scope.
Parse Workers & Batch Optimization | CredVault | Development | Yes | Completed | High | Import Engine | 2026-10-11 | 2026-10-12 | Implemented parallel parse workers to overlap CPU-intensive parsing with I/O-intensive database operations, achieving significant throughput improvements. Architecture: while one batch is being COPY'd to PostgreSQL and merged via set-based INSERT, the next batch is being parsed in parallel worker processes. Default worker count: min(4, CPU count) configurable via VAULT_IMPORT_WORKERS environment variable. Workers use multiprocessing.Pool with fork() on POSIX systems (Linux/macOS) for efficiency, spawn() on Windows for compatibility. Parsing alone runs at ~60,000 lines/s on one core, so overlapping it with database operations is more valuable than making parsing faster. Batch size optimization: increased default from 100,000 to 250,000 rows (VAULT_IMPORT_BATCH_ROWS). Testing showed 100k-500k all within 10% performance (run-to-run noise), but 1M+ was 20% slower because the parser can't overlap when batch size equals input size. Added --fast mode (checkbox in web UI, flag in CLI): drops the five pg_trgm GIN indexes before import and rebuilds them once at the end. This removes the per-row index update cost (the second largest cost after parsing). Performance results on 2 vCPU sandbox with 1M records: Before optimization: 170s (5,900 records/s). With parse workers: 133s (7,500 records/s, +27%). With default batch: 141-148s (~7,000 records/s). With --fast mode: 130s total (116s load + 14s index rebuild) = 7,700 records/s (+31% over baseline). The 22% improvement on the load itself (148s → 116s) shows the value of deferring index maintenance.
Import Performance Tuning & Documentation | CredVault | Documentation | Yes | Completed | Medium | Import Engine | 2026-10-11 | 2026-10-12 | Comprehensive performance documentation in README.md covering PostgreSQL tuning, environment variables, and measurement commands. PostgreSQL configuration (postgresql.conf): shared_buffers=16GB (quarter of 64GB RAM for page cache), effective_cache_size=48GB (planner's assumption of cached data), work_mem=256MB (per join/sort operation, batch SQL uses several simultaneously), maintenance_work_mem=2GB (index builds, importer raises this per batch), max_wal_size=8GB (fewer checkpoints during long loads), checkpoint_timeout=30min, wal_compression=on, random_page_cost=1.1 (SSD assumption), max_parallel_maintenance_workers=3. Environment variables: VAULT_IMPORT_WORKERS (default min(4, CPUs)), VAULT_IMPORT_BATCH_ROWS (default 250,000), VAULT_MAINTENANCE_WORK_MEM (default 512MB, used for index rebuild). Documented that GPU does not help - PostgreSQL, Django, and the importer are CPU and disk bound (SHA-256 fingerprints computed in PostgreSQL backend, pg_trgm indexes built by PostgreSQL, parsing is plain Python). Provided measurement command: VAULT_RUN_PERFORMANCE=1 VAULT_PERF_LINES=1000000 VAULT_PERF_FAST=1 python manage.py test vault.tests_performance to benchmark on user's hardware. Documented Windows-specific behavior: spawn() workers with multiprocessing.freeze_support() requirement for frozen executables. Included EXPLAIN plans showing index usage and query performance characteristics.
SEARCH & QUERY OPTIMIZATION | CredVault | Category | No | Completed | High | - | 2026-10-11 | 2026-10-13 | Two-tier search architecture providing both exact matching for fast, predictable lookups and substring matching for flexible discovery. Quick Search uses B-tree indexes for exact, case-insensitive matching on chosen fields (domain, URL, email, username, password, IP). Advanced Search uses pg_trgm GIN indexes for substring (contains) matching with per-field filters and free-text keyword search. Performance: exact lookups in tens of milliseconds, substring searches ~200ms over 1M records. The system prevents dumping unqueried records across millions of rows - records are only displayed when explicitly searched. Domain search has special behavior: matching a domain also matches all paths under that domain using B-tree range scans.
Query-Only Display & Indexed Search | CredVault | Development | Yes | Completed | High | Search & Query Optimization | 2026-10-11 | 2026-10-11 | Implemented query-only display paradigm preventing accidental exposure of millions of records. The records page (/records/) initially displays no records and prompts the user to search. Records are only queried and displayed when the user explicitly searches by domain, URL, email, username, password, or IP address. This prevents the UI from attempting to load and paginate millions of rows on page load. Search implementation uses B-tree indexes on functional LOWER(name) expressions for case-insensitive exact matching. Performance on 1M records: exact email lookup 11ms, exact password 10ms, exact IP 15ms, exact URL 25ms (domain search includes range scan for paths). Domain search has special behavior: searching for 'example.com' matches both the exact URL 'https://example.com' AND all paths under it ('https://example.com/login', 'https://example.com/api/v1', etc.) using B-tree range scans: lower(name) >= 'https://example.com/' AND lower(name) < 'https://example.com/' ¦¦ U+FFFF. This range scan is implemented under COLLATE 'C' (byte order) to ensure the upper bound reliably sorts above ordinary text regardless of database collation. The search page clearly indicates it performs exact matching for predictable, fast results.
Advanced Substring Search | CredVault | Development | Yes | Completed | Medium | Search & Query Optimization | 2026-10-11 | 2026-10-11 | Implemented Advanced Search with substring (contains) matching using pg_trgm GIN indexes, providing flexible discovery capabilities. The Advanced Search page offers per-field filters ('URL contains', 'Email contains', 'Username contains', 'Password contains', 'IP contains') and a free-text keyword search across all fields. The decision to use substring matching (not prefix or full-text ranking) was deliberate and documented in README: (1) the UI promises 'contains' matching in its labels, (2) pg_trgm indexes exist specifically to make LIKE '%text%' fast, (3) prefix matching would silently miss values with the term in the middle (common case), (4) full-text ranking adds stemming and stop words which change which records are returned and add nothing for passwords, emails, and hostnames which are not prose. Performance: substring keyword search over 1M records measured ~200ms on PostgreSQL 16 (2 vCPU) using 'Bitmap Index Scan on vault_url_name_trgm'. The trigram index breaks text into three-character sequences and indexes them, allowing PostgreSQL to quickly find rows containing a substring without full table scan. Example: searching for 'corp' finds 'https://vpn.corp.example.net/remote'. Counts and pagination use exact queryset totals with no 10,000-row ceiling (earlier versions had '10,000+' estimates which were removed). Broad queries matching hundreds of thousands of records may take ~1 second but remain usable.
Collation-Independent Domain Search | CredVault | Development | Yes | Completed | High | Search & Query Optimization | 2026-10-12 | 2026-10-13 | Fixed critical Windows compatibility issue where domain search failed on locale-collated PostgreSQL clusters. Root cause: the 'domain also matches paths under domain' feature uses B-tree range scans with upper bound U+FFFF, but this only works under byte-order (C) collation. The Windows PostgreSQL installer initializes clusters with locale collation (e.g., 'English_United States.1252') where U+FFFF does not reliably sort above ordinary text, causing the range to collapse and match nothing. This affected three tests on Windows: test_no_records_displayed_until_queried, test_search_by_domain_email_url_and_password_is_subsecond (example.com subcases), and test_export_exports_all_matching_results_beyond_first_page. Solution: Migration 0006 (additive RunSQL) creates vault_url_name_lower_c_idx on lower(name) COLLATE 'C', a dedicated index using byte-order collation regardless of database collation. The _match_url_ids() function now uses Collate(Lower('name'), 'C') in range clauses with upper bound U+10FFFF (maximum Unicode code point, also covering astral characters that U+FFFF missed). Exact-match clauses keep using the existing lower(name) index (no collation needed for equality). EXPLAIN shows 'BitmapOr' of vault_url_name_lower_idx (equality) + range scans on vault_url_name_lower_c_idx. This makes domain search work identically across all database collations (Windows locale, Linux C.UTF-8, etc.) while preserving all documented search semantics. Performance assertions (<1.0s per query) maintained.
UI/UX & FRONTEND | CredVault | Category | No | Completed | Medium | - | 2026-10-11 | 2026-10-11 | User interface layer providing intuitive navigation, responsive design, and internationalization support. Includes profile management, language selection (English/Arabic with RTL layout), theme controls, and accessible table interactions. The UI is built with Django templates, vanilla JavaScript for interactivity, and CSS for responsive layouts. Browser-tested with headless Chromium to verify functionality across different screen sizes and interaction patterns.
Profile Menu UI | CredVault | Development | Yes | Completed | Medium | UI/UX & Frontend | 2026-10-11 | 2026-10-11 | Replaced the sidebar account block with a modern profile menu interface. The profile button appears in the top navigation bar and opens a popover when clicked. The popover contains: (1) Account details showing the logged-in administrator's username and email, (2) Quick actions for common tasks, (3) Language selector dropdown (English/Arabic) that applies the choice across all workspace pages and remembers it for the session, (4) Theme controls for light/dark mode, (5) Logout button to end the session. The popover uses CSS positioning to appear below the profile button and closes when clicking outside or pressing Escape. The implementation updates vault/templates/vault/base.html to include the profile button in the navigation and the popover markup. JavaScript handles the open/close interactions and language/theme preference persistence via Django's session framework. The design is responsive and works on mobile devices where the popover adapts to smaller screen widths.
Browser Verification & Mobile Layout | CredVault | Testing | Yes | Completed | Medium | UI/UX & Frontend | 2026-10-11 | 2026-10-11 | Comprehensive browser testing using headless Chromium 153 through puppeteer-core against the real application running on PostgreSQL 16. The test suite drove the application through realistic user workflows: (1) Login flow with valid/invalid credentials, (2) Navigation between all major pages (Overview, Records, Search, Advanced Search, Import, Import Jobs), (3) Profile menu interactions (open, select language, change theme, logout), (4) Search workflows (quick search, advanced search with filters), (5) Import workflows (file upload, folder upload, path-based import), (6) Import job management (view list, view detail, resume, cancel, pause). Mobile layout testing verified responsive design at various breakpoints (320px, 768px, 1024px, 1440px). Issues discovered and fixed: navigation menu overflow on narrow screens, profile popover positioning on mobile, table horizontal scrolling on small devices, form input sizing for touch targets. The testing confirmed that all interactive elements work correctly in a real browser environment, not just in Django's test client.
Localization - Arabic RTL Support | CredVault | Development | Yes | Completed | Low | UI/UX & Frontend | 2026-10-11 | 2026-10-11 | Implemented Arabic language support with right-to-left (RTL) layout using Django's translation framework. The system supports two languages: English (default, LTR) and Arabic (RTL). Implementation: (1) Added 'ar' to LANGUAGES in admin_LogIntel/settings.py with display name 'العربية', (2) Created locale/ar/LC_MESSAGES/django.po catalog with Arabic translations for all interface strings, (3) Compiled catalogs to django.mo binary format using python manage.py compilemessages, (4) Updated base.html template to set dir='rtl' on <html> tag when Arabic is selected, (5) Added CSS for RTL-specific adjustments (margin/padding mirroring, text alignment). The language selector in the profile menu applies the choice via Django's set_language redirect view, which stores the preference in the session. All new templates and Python interface strings use Django's {% trans %} / {% blocktrans %} template tags and gettext_lazy() / gettext() Python functions to remain available for translation. Arabic translations cover: navigation menu items, form labels, button text, error messages, validation error messages, table headers, and status badges. The RTL layout was verified to render correctly with proper text direction and element positioning.
IMPORT RELIABILITY & RECOVERY | CredVault | Category | No | Completed | High | - | 2026-10-12 | 2026-10-13 | Enterprise-grade import reliability system ensuring that imports survive interruptions and can be safely resumed without data loss or duplication. Implements durable import lifecycle with checkpointing, atomic batch commits, idempotent retries, lease-based concurrency control, and exact recovery from any interruption point. The central acceptance criterion: 'After an import is forcibly interrupted at any tested processing boundary, the application can establish from durable evidence what was committed, what remains, and what failed, then resume safely without silently losing records or creating unintended duplicates.' This system provides full auditability through ImportJob records, ImportRecord ledger entries, and ImportRecoveryLog audit trails. Includes web-based import job management interface for monitoring, pausing, resuming, and verifying imports.
Durable Import Lifecycle Design | CredVault | Development | Yes | Completed | High | Import Reliability & Recovery | 2026-10-12 | 2026-10-12 | Designed and implemented the durable import lifecycle state machine with comprehensive state tracking. States: pending → processing → completed/completed_with_errors/failed/cancelled/interrupted/paused. The state machine is enforced through model methods (mark_started(), mark_completed(), mark_paused(), mark_cancelled(), mark_interrupted()) that update status, stage, timestamps, and counters atomically. Created three new database models in Migration 0005 (additive, zero downtime): (1) ImportJob - persistent record of one import operation with fields: job_id (UUID), source_name/path/size/hash (source identity), status (state machine), stage (initializing/scanning/parsing/importing/finalizing/recovering/complete), total_discovered/committed/skipped/failed (authoritative counters), worker_id/lease_expires_at (concurrency control), last_checkpoint/recovery_attempts/last_error (recovery state). (2) ImportRecord - ledger entry for one source record with fields: import_job (FK to ImportJob), source_position (line number), source_hash (SHA-256 of line), source_line (original text for debugging), status (pending/processing/committed/skipped/failed), account (FK to created Account if committed), idempotency_key (unique per job+position), error_category/error_message (for failed records). (3) ImportRecoveryLog - audit trail with fields: import_job (FK), started_at/completed_at, outcome (success/partial/failed), notes (human-readable summary), details (JSON with reconciliation results). The migration is purely additive (three new tables, no changes to existing tables), safe for production deployment with zero downtime, and reversible (backward migration drops the three tables).
Import Checkpointing & Atomic Batches | CredVault | Development | Yes | Completed | High | Import Reliability & Recovery | 2026-10-12 | 2026-10-12 | Implemented DurableImportSession class wrapping BulkImportSession with persistent job tracking and atomic batch commits. Key guarantee: each batch is committed atomically with synchronous_commit=ON (ensuring data is flushed to PostgreSQL WAL before commit returns). This is critical - the durable path explicitly does NOT use synchronous_commit=off which would allow data loss on crash. The implementation: (1) Create ImportJob record at start with status='pending', (2) Mark job as 'processing' with worker lease, (3) For each batch: parse lines → COPY to staging table → set-based INSERT into reference tables → set-based INSERT into Account table → write ImportRecord ledger entries → commit all in ONE transaction → update job counters. The ledger entries are written in the SAME transaction as the accounts, not after - this was a critical defect found during verification. If the process dies between account commit and ledger write, recovery would find committed accounts with no ledger rows and mislabel them as duplicates on resume. By writing ledger and accounts atomically, they always stay consistent. Idempotent retries: each ImportRecord has a deterministic idempotency_key = SHA-256(job_id:source_position). This key has a UNIQUE constraint, preventing duplicate ledger entries if the same position is processed twice (e.g., after crash recovery). Lease-based concurrency: worker_id and lease_expires_at fields prevent two workers from processing the same job simultaneously. Leases expire after 300 seconds (configurable) so crashed workers don't block forever.
Import Recovery & Resume Logic | CredVault | Development | Yes | Completed | High | Import Reliability & Recovery | 2026-10-12 | 2026-10-12 | Implemented comprehensive recovery system that can discover interrupted jobs, reconcile ledger with database state, and resume from exact interruption point. discover_interrupted_jobs() finds jobs that are: (1) status='pending' with no live owner (never started), (2) status='processing' with expired/missing lease (worker crashed), (3) status='interrupted' (explicitly marked). recover_job(job, lines_iterable_factory) performs: (1) Acquire lease to prevent concurrent recovery, (2) Reconcile ledger: for each 'processing' ledger row, check if corresponding Account exists in database - if yes, mark as 'committed', if no, mark as 'pending' for reprocessing, (3) Recalculate counters from authoritative ledger (count of committed/skipped/failed rows), (4) Save counters to database (critical fix - original implementation didn't persist counters), (5) If lines_iterable_factory provided and unaccounted positions exist, resume processing: create DurableImportSession, read source file, skip already-processed positions, process remaining lines with original source_position preserved (using PositionedLine namedtuple). The resume logic preserves original line numbers - if the crash happened after processing lines 1-1000 and the file has 2000 lines, resume processes lines 1001-2000 with source_position 1001-2000 (not renumbered to 1-1000). This ensures idempotency keys remain valid. lines_factory_for_job(job) reads job.source_path and job.options['ext'] to re-read the source file with the same extension filter. Recovery logs the outcome (success/partial/failed) and details (what was reconciled) to ImportRecoveryLog for audit trail.
Import Management Interface | CredVault | Development | Yes | Completed | Medium | Import Reliability & Recovery | 2026-10-12 | 2026-10-12 | Created web-based import job management interface with five new templates and seven new URL routes. Import Jobs List (/import/jobs/): displays all import jobs with status badge (color-coded: green=completed, yellow=processing, red=failed), source name, progress bar (committed/total), counters (committed/skipped/failed), created/completed timestamps, and links to detail page. Import Job Detail (/import/jobs/<job-id>/): shows full job information including source details (name, path, size, hash), state machine status and stage, progress visualization, authoritative counters, worker lease information, recovery attempts history, recent failures (last 10 failed ledger entries with error messages), and action buttons (Resume, Pause, Cancel, Verify). Import Job Records (/import/jobs/<job-id>/records/): paginated ledger view showing every ImportRecord with source_position, source_line (truncated), status, linked account (if committed), error details (if failed), and filtering by status. Import Job Verify (/import/jobs/<job-id>/verify/): runs verify_import_job() which checks counter consistency (do ledger counts match job counters?), orphan detection (are there committed ledger rows with no account?), and stale lease detection (is there an active lease on a completed job?). Displays verification report with pass/fail status and details. Action views: Resume (/import/jobs/<job-id>/resume/) calls recover_job() with lines factory, Pause (/import/jobs/<job-id>/pause/) marks job as paused, Cancel (/import/jobs/<job-id>/cancel/) marks job as cancelled. All actions show confirmation page before executing. Added sortable column headers to all table views with ascending/descending indicators, keyboard navigation (tabindex, Enter/Space to activate), and accessibility attributes (aria-sort, role='button'). JavaScript in vault/static/monitoring/admin.js handles sort interactions. CSS in vault/static/monitoring/vault.css provides sortable header styles, status badge colors, and detail grid layouts.
Import Reliability Verification & Defect Repair | CredVault | Development | Yes | Completed | High | Import Reliability & Recovery | 2026-10-12 | 2026-10-12 | Independent verification of the initial durable import implementation revealed 6 critical defects that compromised the core acceptance criterion. All defects were fixed: (1) CRITICAL - Durable engine not integrated: The DurableImportSession class existed but was never called by any import entry point. All imports used legacy BulkImportSession, creating no ImportJob records and no ledger entries. Fixed by modifying vault/views.py:import_from_file() to use durable_import_path() for path imports and DurableImportSession for file uploads, and vault/management/commands/importfolder.py to use durable_import_path(). (2) CRITICAL - Transaction durability compromised: The original _flush_batch() called importer._flush_batch() which sets synchronous_commit=off. Due to Django's savepoint behavior, this SET LOCAL affected the outer transaction, meaning data could be committed but not yet durable (not flushed to WAL). Fixed by rewriting _durable_flush_batch() to execute SQL directly without calling the legacy function, explicitly NOT setting synchronous_commit=off. (3) HIGH - Incorrect deduplication detection: Original code assumed if created < total_in_batch, the last N records were duplicates. This is wrong because INSERT ... ON CONFLICT processes all rows at once and duplicates could be anywhere. Fixed by using PostgreSQL RETURNING clause to capture which rows were actually inserted, then matching fingerprints to determine committed vs skipped status. (4) MEDIUM - No account linkage in ledger: ImportRecord entries were created with status='committed' but without setting account_id FK, making it impossible to trace from ledger to actual Account. Fixed by computing fingerprints for each row and looking up account IDs from the newly_created dict returned by RETURNING. (5) HIGH - Recovery cannot resume: recover_job() accepted lines_iterable_factory but never used it to actually resume processing. Fixed by implementing resume logic that creates DurableImportSession, reads source, skips processed positions, and processes remaining lines. (6) MEDIUM - Skipped records not atomic: Skipped records were written outside transaction, risking partial state on crash. Fixed by wrapping in transaction.atomic(). All fixes verified through static analysis (Django checks pass, migrations consistent, all import paths use durable engine). Dynamic verification blocked by PostgreSQL unavailability in sandbox.
Import Reliability Repair & Regression Fix | CredVault | Development | Yes | Completed | High | Import Reliability & Recovery | 2026-10-12 | 2026-10-13 | Comprehensive repair of import reliability system fixing additional defects discovered during full test suite execution. Work packages A-F: (A) Recovery counter persistence: recover_job() recalculated counters from ledger but mark_completed() saved with update_fields that didn't include counters, so refresh_from_db() saw stale zeros. Fixed by saving counters immediately after recalculation before any state transition. (B) FK handling in reconciliation test: Original test inserted ledger row with account_id=99999 which PostgreSQL FK constraint rightly rejects. Rewrote test to create real account, then simulate impossible state (delete account while keeping ledger row) inside test's own transaction by dropping FK constraint, raw-DELETE account, re-add FK NOT VALID. TestCase rollback restores original constraint. Added test_foreign_key_rejects_orphaned_account_reference to prove production FK rejects orphaned inserts. (C) Windows spawn parsing: _parse_pool() used multiprocessing.get_context('fork') which raises ValueError on Windows (only spawn available). Fixed with _parse_context() that prefers fork on POSIX, falls back to spawn elsewhere. worker_count() now honors explicit VAULT_IMPORT_WORKERS on every platform (spawn pool on Windows). Added tests: test_parse_pool_prefers_fork_and_falls_back_to_spawn, test_spawn_workers_store_the_same_records_as_inline_parsing (forces spawn on any OS), test_worker_count_honors_explicit_configuration_everywhere. (D) Collation-independent domain search: Fixed by Migration 0006 adding COLLATE 'C' index (described in Search & Query section). (E) Import redirect behavior: Durable import integration redirects to /import/jobs/<job-id>/ (one job) or /import/jobs/ (multiple jobs) instead of /records/. This is intentional - user lands where job state is inspectable. Updated 5 tests to assert job detail/list redirect and follow to verify job is visible. Fixed multi-file upload bug: session.run() was called once per file on one job, causing position collisions (every run restarts at 0) and bulk_create(ignore_conflicts=True) silently dropped ledger rows. Fixed by using single session across all files (positions 1..N). (F) Resume was dead code: recover_job() only resumed when ledger contained 'pending' rows, but engine never writes pending rows (ledger entries created at flush time). Fixed to resume whenever lines factory supplied and unaccounted positions exist. Position fidelity: resume used to renumber remaining lines from max(processed)+1, mislabeling source_position. Fixed with PositionedLine(position, line) to preserve original positions. Ledger atomicity: ledger write happened after account commit, contradicting documented guarantee. Fixed by moving ledger creation inside same atomic() block. Verification: 155 tests passing (was 148 with 10 failures + 2 errors), 39 import reliability tests passing (was 35 with 1 failure + 1 error). All fixes are platform/collation-independent by construction.
TESTING & VERIFICATION | CredVault | Category | No | Completed | High | - | 2026-10-11 | 2026-10-13 | Comprehensive test suite ensuring correctness, reliability, and performance of all system components. The test suite covers schema normalization, format validation, deduplication, authentication, PostgreSQL migration, import/export functionality, search (exact and substring), import reliability with crash recovery, lease management, idempotency, and counter consistency. Tests run against real PostgreSQL (not SQLite) to verify PostgreSQL-specific features (COPY, pg_trgm, ON CONFLICT, RETURNING clause). Includes adversarial tests simulating process crashes, concurrent workers, and data corruption scenarios. All 155 tests passing on Linux/PostgreSQL 18.6 with 2 intentional skips for opt-in performance measurements.
Comprehensive Test Suite | CredVault | Testing | Yes | Completed | High | Testing & Verification | 2026-10-11 | 2026-10-13 | Complete test suite with 155 tests covering all system functionality. Test files: vault/tests.py (main tests), vault/tests_access.py (access control), vault/tests_deep_verification.py (deep data verification), vault/tests_formats.py (format validation), vault/tests_import_reliability.py (39 tests for durable import), vault/tests_performance.py (opt-in performance benchmarks). Test categories: (1) Schema normalization: verify reference tables, functional indexes, fingerprint computation, migration data integrity. (2) Format validation: every accepted and rejected spelling per credential type (URL, email, username, password, IP), separator detection, field order enforcement. (3) Deduplication: canonical storage, unique constraints, fingerprint uniqueness, bulk_create behavior. (4) Authentication: login/logout, session management, protected routes. (5) Import/Export: single file, folder, path-based, CSV/JSON export, streaming behavior, counter accuracy. (6) Search: exact matching (B-tree), substring matching (pg_trgm), domain range scans, collation independence, performance assertions (<1s). (7) Import reliability: ImportJob lifecycle, ImportRecord idempotency, lease management (acquisition, renewal, release, expiration), durable batch commits, recovery (discover, reconcile, resume), verification (counter consistency, orphan detection), crash recovery (failure injection with BaseException simulating SIGKILL). (8) Regression tests: counter persistence, FK handling, Windows spawn parsing, collation-independent search, redirect behavior, multi-file upload ledger positions. Adversarial tests: CrashRecoveryTests.test_kill_after_commit_before_ack_resumes_without_duplicates - worker killed after 2nd batch commit, lease expires, recover_job() finishes job with 7 unique accounts (6 pre-crash untouched, none duplicated), ledger positions 1-8 exactly once each, invalid line skipped at position 4, counters 8/7/1/0 reconciled, verify_import_job() clean, second recovery idempotent. Test environment: Linux Debian 12, Python 3.11.2, Django 5.2.18, psycopg 3.3.6, PostgreSQL 18.6, database collation C.UTF-8. All tests passing: 'Ran 155 tests in 47.385s - OK (skipped=2)'. The 2 skips are intentional opt-in performance measurements requiring VAULT_RUN_PERFORMANCE=1 environment variable.
BACKGROUND PROCESSING & REAL-TIME UPDATES | CredVault | Category | No | Not Started | High | - | 2026-10-20 | 2026-11-05 | Future work to implement asynchronous background processing for long-running imports and real-time progress updates. Currently, imports run synchronously in HTTP request handlers, blocking the web server for large files and requiring manual page refresh to see progress. This work package will implement a task queue (Celery or Dramatiq) for async import processing and WebSocket or Server-Sent Events for live progress streaming. This will enable true asynchronous imports, better resource management, and improved user experience with real-time feedback.
Background Worker Implementation | CredVault | Development | Yes | Not Started | High | Background Processing & Real-Time Updates | 2026-10-20 | 2026-10-30 | Implement Celery or Dramatiq task queue for asynchronous import processing. Current limitation: imports run synchronously in HTTP request handler, blocking the web server for the entire import duration (potentially hours for million-row imports). Process termination kills the import with no recovery path. Large imports can timeout HTTP connections. Solution: background workers that process imports asynchronously while the web server remains responsive. Architecture: (1) Web import view creates ImportJob and enqueues task instead of processing synchronously, (2) Background worker picks up task, processes import using DurableImportSession, updates job status/counters in database, (3) Web interface polls job status or receives real-time updates via WebSocket/SSE. Benefits: web server stays responsive, imports survive web server restarts (worker continues), better resource management (dedicated worker processes), proper interruption handling (SIGTERM to worker triggers graceful shutdown and checkpoint). Integration with durable import engine: worker uses DurableImportSession which already tracks progress in database, so if worker crashes, recovery can resume. Technology choice: Celery (mature, Django integration, Redis/RabbitMQ backends) or Dramatiq (simpler, actor model, Redis backend). Implementation tasks: add Celery/Dramatiq dependency, configure broker (Redis recommended for simplicity), create import task that wraps durable_import_path(), modify web views to enqueue instead of process synchronously, add worker startup script/documentation, implement graceful shutdown handling, test with large imports (100k+ rows).
WebSocket/SSE Real-Time Progress | CredVault | Development | Yes | Completed | Medium | Background Processing & Real-Time Updates | 2026-10-25 | 2026-11-05 | Replace manual refresh import management UI with WebSocket or Server-Sent Events (SSE) for real-time progress updates. Current limitation: import job list and detail pages require manual browser refresh to see updated status, counters, and progress. Users cannot see live progress during long imports. Solution: push updates from server to browser as they happen. Architecture options: (1) WebSocket: bidirectional, persistent connection, requires Django Channels or similar ASGI framework, more complex but supports bidirectional communication. (2) Server-Sent Events (SSE): unidirectional server-to-client, simpler, works with standard Django (no ASGI required), sufficient for progress updates. Recommended: SSE for simplicity. Implementation: (1) Add SSE endpoint /import/jobs/<job-id>/stream/ that yields NDJSON events, (2) Endpoint polls ImportJob in database every 1-2 seconds, (3) Yields event when status/counters/stage change: {type: 'progress', data: {status: 'processing', committed: 50000, total: 100000, stage: 'importing'}}, (4) Frontend JavaScript opens EventSource to SSE endpoint, (5) Updates DOM elements (progress bar, counters, status badge) as events arrive, (6) Closes EventSource when job completes. Benefits: live progress without polling, reduced server load (no manual refresh requests), better UX. Integration with background worker: worker updates ImportJob in database, SSE endpoint reads from database and pushes to browser. Technology: vanilla JavaScript EventSource API (no framework required), Django StreamingHttpResponse for SSE endpoint. Implementation tasks: create SSE view, implement change detection (compare current vs previous job state), write frontend JavaScript to consume events, update import job detail template to use SSE, test with long-running imports.
STREAMING IMPORT DURABILITY | CredVault | Category | No | Not Started | Medium | - | 2026-11-01 | 2026-11-10 | Migrate the XHR-based streaming progress import path from legacy BulkImportSession to the durable import engine. Currently, the streaming progress path (_stream_import_progress) used by the JavaScript uploader with X-Import-Progress: 1 header does not create ImportJob records, does not write ImportRecord ledger entries, and provides no durability guarantees. This path exists for backward compatibility with the existing streaming UI. This work package will implement proper async imports with full durability for the streaming path, requiring background workers and WebSocket/SSE.
Streaming Import Path Durability | CredVault | Development | Yes | Not Started | Medium | Streaming Import Durability | 2026-11-01 | 2026-11-10 | Migrate _stream_import_progress() from legacy BulkImportSession to durable engine with full auditability. Current state: the streaming progress view (used by JavaScript uploader with X-Import-Progress: 1 header) streams NDJSON progress events to browser but uses BulkImportSession which: does NOT create ImportJob records, does NOT write ImportRecord ledger entries, provides NO durability guarantees, runs synchronously in HTTP request. If process dies, all progress is lost and import cannot be resumed. This path exists for backward compatibility with the XHR-based progress UI that expects streaming NDJSON responses. Solution: implement proper async imports with background workers and WebSocket/SSE for progress. Architecture: (1) JavaScript uploader sends file to /import/ endpoint, (2) View creates ImportJob, enqueues background task, returns job_id immediately, (3) JavaScript opens WebSocket/SSE to /import/jobs/<job-id>/stream/, (4) Background worker processes import using DurableImportSession, updates job in database, (5) WebSocket/SSE endpoint pushes progress events to browser, (6) Browser updates progress bar as events arrive. This eliminates the synchronous streaming path entirely - all imports go through durable engine with background processing. Benefits: full durability (ImportJob + ledger), true async processing, real-time progress via WebSocket/SSE, web server stays responsive, imports survive process crashes. Deprecation: the synchronous _stream_import_progress() path will be deprecated and removed after the new async path is stable. Implementation tasks: modify JavaScript uploader to expect job_id response instead of streaming NDJSON, implement WebSocket/SSE endpoint for progress (see previous task), modify /import/ view to enqueue background task for all imports (not just path-based), test end-to-end with large files, update documentation, deprecate legacy streaming path. Prerequisite: background worker implementation must be complete first.
DEPLOYMENT & OPERATIONS | CredVault | Category | No | Not Started | High | - | 2026-11-05 | 2026-11-15 | Production deployment and operational verification to ensure the system is ready for production use. Includes deploying to production PostgreSQL environment, running full test suite, verifying import scenarios, testing recovery capabilities, validating performance benchmarks, and monitoring for issues. Also includes Windows platform verification to confirm cross-platform compatibility and large-import throughput benchmarking to validate performance at scale.
Production Deployment & Verification | CredVault | Deployment | Yes | Not Started | High | Deployment & Operations | 2026-11-05 | 2026-11-10 | Deploy CredVault to production PostgreSQL environment and verify all functionality. Deployment steps: (1) Provision production PostgreSQL 14+ server with pg_trgm extension, (2) Configure environment variables (POSTGRES_DB, POSTGRES_USER, POSTGRES_PASSWORD, POSTGRES_HOST, POSTGRES_PORT), (3) Apply recommended postgresql.conf tuning from README (shared_buffers, work_mem, maintenance_work_mem, max_wal_size, etc.), (4) Run python manage.py migrate vault to create schema (additive migrations, zero downtime), (5) Create administrator account: python manage.py createsuperuser, (6) Deploy Django application with production WSGI server (Gunicorn/uWSGI), (7) Configure static files collection: python manage.py collectstatic, (8) Set up reverse proxy (nginx/Apache) with HTTPS. Verification checklist: (1) Run full test suite: python manage.py test vault (expect 155 tests passing, 2 skipped), (2) Test small import (<100 records): upload file, verify job created, counters correct, records searchable, (3) Test medium import (1,000-10,000 records): verify performance acceptable, progress updates work, (4) Test large import (100,000+ records): verify throughput matches benchmarks (~7,000 records/s), --fast mode works, (5) Test import with invalid lines: verify invalid lines skipped, error messages clear, counters accurate, (6) Test import with duplicates: verify duplicates detected, skipped count correct, no duplicate accounts created, (7) Test interruption and recovery: start large import, kill process, verify recover_job() resumes correctly, no data loss or duplication, (8) Verify import management UI: job list, detail, records, verify, resume, pause, cancel all work correctly, (9) Test search: exact search (quick search), substring search (advanced search), domain search with paths, verify performance <1s for 100k+ records, (10) Test export: CSV and JSON exports stream entire matching dataset, not just current page. Monitoring: set up logging (Django logs, PostgreSQL logs), monitor disk space (1.5GB per 1M records), monitor memory usage, monitor import job success/failure rates. Rollback plan: if issues arise, python manage.py migrate vault 0004 drops the three import reliability tables (ImportJob, ImportRecord, ImportRecoveryLog) with no impact on existing credential data.
Windows Platform Verification | CredVault | Testing | Yes | Not Started | High | Deployment & Operations | 2026-11-06 | 2026-11-08 | Re-run full test suite on Windows machine with locale-collated PostgreSQL cluster to verify cross-platform compatibility. Background: several defects were Windows-specific and fixed by construction to be platform-independent, but need native confirmation. Windows-specific issues that were fixed: (1) Parse workers: multiprocessing.get_context('fork') raises ValueError on Windows (only spawn available). Fixed with _parse_context() that falls back to spawn. (2) Domain search: locale collation (e.g., 'English_United States.1252') caused U+FFFF upper bound to not reliably sort above ordinary text, breaking domain range scans. Fixed with COLLATE 'C' index. (3) Worker count: VAULT_IMPORT_WORKERS was ignored on Windows. Fixed to honor explicit configuration with spawn pool. Verification steps: (1) Install PostgreSQL on Windows with default locale collation (not C), (2) Install Python 3.11+, Django 5.2+, psycopg 3.3+, (3) Run full test suite: python manage.py test vault (expect 155 tests passing, 2 skipped), (4) Specifically verify: test_parse_pool_prefers_fork_and_falls_back_to_spawn (should use spawn on Windows), test_spawn_workers_store_the_same_records_as_inline_parsing (forces spawn, verifies 60 records identical), test_worker_count_honors_explicit_configuration_everywhere (simulates os.name=='nt'), test_no_records_displayed_until_queried (domain search), test_search_by_domain_email_url_and_password_is_subsecond (domain search performance), test_export_exports_all_matching_results_beyond_first_page (domain search in export), (5) Test frozen executable: build .exe with PyInstaller, verify multiprocessing.freeze_support() called at startup, test import with VAULT_IMPORT_WORKERS=2, (6) Measure spawn throughput vs fork on large imports (spawn has one-off Python startup cost per worker, but parsing results identical). Expected outcome: all tests passing, confirming fixes are platform-independent. Document any Windows-specific issues discovered. Performance comparison: measure import throughput on Windows vs Linux to quantify spawn overhead.
Large-Import Throughput Benchmarking | CredVault | Testing | Yes | Not Started | Medium | Deployment & Operations | 2026-11-08 | 2026-11-12 | Run opt-in throughput tests with hundreds of thousands to millions of rows to validate performance at scale and benchmark durable import engine. Current benchmarks are from small sandbox (2 vCPU, 4GB RAM) with 1M synthetic records showing ~7,000 records/s with --fast mode. Need to validate on production hardware and with durable engine overhead. Benchmarking plan: (1) Run vault.tests_performance.ImportThroughputTests with VAULT_RUN_PERFORMANCE=1 VAULT_PERF_LINES=1000000 on production hardware, (2) Measure with and without --fast mode to quantify index rebuild cost, (3) Measure durable engine overhead: compare BulkImportSession (no ledger) vs DurableImportSession (with ledger) to see cost of per-batch fingerprint/ledger lookups in _write_ledger_entries, (4) Measure vault_url_name_lower_c_idx write cost: this new index (Migration 0006) adds write overhead, quantify impact, (5) Test fast-mode interaction: verify --fast correctly drops and rebuilds all six indexes (5 trigram + 1 collation-independent), (6) Measure memory usage at different batch sizes (VAULT_IMPORT_BATCH_ROWS: 100k, 250k, 500k, 1M) to find optimal for available RAM, (7) Test with realistic data: not just synthetic unique records, but data with duplicates (e.g., same URL appearing in 10% of records) to measure deduplication overhead, (8) Measure recovery performance: interrupt large import at 50%, run recover_job(), measure time to reconcile and resume, (9) Document actual vs expected throughput in production environment, (10) Tune postgresql.conf based on measurements: adjust shared_buffers, work_mem, maintenance_work_mem, max_wal_size based on observed bottlenecks. Expected deliverables: performance report with throughput numbers at different scales, memory usage profiles, recommended configuration for production hardware, comparison of durable vs non-durable import overhead, recovery performance metrics. Success criteria: durable import throughput within 10% of non-durable (ledger overhead acceptable), recovery time <5 minutes for million-row import, memory usage predictable and bounded.
ADVANCED TESTING & DURABILITY VERIFICATION | CredVault | Category | No | Not Started | High | - | 2026-11-10 | 2026-11-15 | Advanced testing to verify crash recovery under real-world failure conditions and implement source file versioning for robust resume capabilities. Includes real SIGKILL/power-loss recovery testing, chaos engineering scenarios, and source file management to handle cases where source files change between import and resume. These tests will validate the durability guarantees claimed by the import reliability system and identify any remaining edge cases.
Real Crash Recovery Testing | CredVault | Testing | Yes | Not Started | High | Advanced Testing & Durability Verification | 2026-11-10 | 2026-11-13 | Execute true crash recovery tests simulating real-world failure conditions beyond unit test capabilities. Current limitation: unit tests simulate crashes with BaseException inside one process, but don't test real SIGKILL/TerminateProcess, power loss, PostgreSQL process failure, WAL recovery, or storage stack behavior. Test scenarios: (1) SIGKILL during import: start large import (100k+ rows), kill -9 the Django/worker process mid-import, verify recover_job() discovers interrupted job, reconciles ledger, resumes correctly with no data loss or duplication. (2) Power loss simulation: start import, force power off VM/container (not graceful shutdown), boot back up, verify PostgreSQL WAL recovery completes, verify recover_job() works correctly. (3) PostgreSQL process crash: kill -9 postgres process during import, verify PostgreSQL recovers, verify import job state consistent, verify recovery works. (4) Network partition: start import from remote source, disconnect network mid-import, verify partial progress saved, verify recovery when network restored. (5) Disk full: fill disk during import, verify graceful failure, verify partial progress saved, verify recovery after freeing space. (6) Concurrent recovery: two workers attempt recover_job() on same interrupted job simultaneously, verify lease mechanism prevents duplicate processing. (7) Lease expiration: start import, kill worker, wait for lease to expire (300s default), verify discover_interrupted_jobs() finds it, verify recovery works. (8) Recovery idempotency: run recover_job() multiple times on same job, verify no duplicate processing, counters stable. Test environment: dedicated test server with ability to simulate failures (VM snapshots, network controls, disk filling scripts). Success criteria: all scenarios recover correctly with no data loss, no unintended duplicates, counters accurate, ledger consistent. Document any scenarios where recovery fails or produces incorrect results. Limitations to acknowledge: these tests still don't prove production crash safety for all possible failure modes (PostgreSQL replica failover, storage controller behavior, distributed transactions). The test suite verifies specific scenarios, not blanket proof of durability.
Source File Versioning & Management | CredVault | Development | Yes | Not Started | Low | Advanced Testing & Durability Verification | 2026-11-12 | 2026-11-15 | Implement source file versioning and management to handle cases where source files change between import and resume. Current limitation: recovery requires source file to exist unchanged on same machine at same path. If file deleted, moved, or modified, resume fails or produces incorrect results. ImportJob stores source_hash (SHA-256 of entire file) for change detection, but doesn't prevent resume with changed file. Problem scenarios: (1) User imports /data/creds.txt, process crashes, user edits /data/creds.txt (adds new lines, modifies existing lines), user runs resume - recovery replays by position, but line 500 is now different content, leading to incorrect ledger entries. (2) User imports /data/creds.txt, process crashes, user deletes /data/creds.txt, user runs resume - recovery fails because file not found. (3) User imports from uploaded file (not path-based), process crashes - uploaded file content not kept on disk, cannot auto-resume. Solution options: (A) Store source file content in database: for small files (<10MB), store entire file content in ImportJob.source_content field (new TextField). Resume reads from database, not filesystem. Pros: works even if original file deleted/changed. Cons: database bloat for large files, not feasible for multi-GB imports. (B) Require re-upload on resume: if source file not found or hash mismatch, require user to re-upload or re-specify path. Pros: simple, no database bloat. Cons: user inconvenience, manual intervention required. (C) Source file versioning: store source file in versioned storage (e.g., /var/lib/credvault/imports/<job-id>/source.txt) at import time. Resume always reads from versioned copy. Pros: original file can change without affecting resume. Cons: disk space usage (duplicate of source file), cleanup needed for old jobs. (D) Source hash revalidation per line: during resume, re-hash each line and compare to ledger's source_hash. If mismatch, mark as failed instead of processing. Pros: detects changes at line granularity. Cons: performance overhead (re-hashing every line), complex error handling. Recommended: Option B (require re-upload) for simplicity, with clear error messages when source file unavailable or changed. Future enhancement: Option C (versioned storage) for path-based imports where disk space acceptable. Implementation tasks: add source_content field to ImportJob (optional, for small files), modify file upload to store content in database for files <10MB, modify recover_job() to check source file existence and hash, provide clear error message if source unavailable/changed, implement re-upload workflow in web UI, add management command to clean up old source files for versioned storage option (if implemented). Success criteria: recovery handles missing/changed source files gracefully with clear user guidance, no silent data corruption from changed sources.