## Project Overview
CredVault Project Overview
Project Name | CredVault
Status | In Progress
Project Type | Web Application - Credential Vault Management System
Priority | Medium
Expected Start Date | 2026-10-11
Expected Completion Date | 2026-11-15
Project Description
CredVault is a Django-based credential vault management system designed for secure storage and retrieval of URLs, emails, usernames, passwords, and IP addresses. The system enforces strict data validation, prevents duplicates through SHA-256 fingerprinting, and provides high-performance bulk import capabilities with PostgreSQL backend. Key features include durable import lifecycle with checkpointing and recovery, sub-second indexed search, administrator authentication, and comprehensive audit trails.

## Task Tracker
Subject / Task | Project | Type | Part of Group | Status | Priority | Main Task (Parent) | Expected Start Date | Expected Completion Date | Details and Task Description
Schema Normalization & Reference Tables | CredVault | Development | Yes | Completed | High | Data Architecture | 2026-10-11 | 2026-10-11 | Replaced flat Record model with five deduplicated reference tables (Url, Email, User, Pass, Ip) linked by Account. Each table has name, created_at, updated_at fields with functional LOWER(name) B-tree indexes for case-insensitive uniqueness.
SHA-256 Fingerprint Implementation | CredVault | Development | Yes | Completed | High | Data Architecture | 2026-10-11 | 2026-10-11 | Implemented unique Account.fingerprint using SHA-256 hash of six columns (url_id, email_id, user_id, pass_id, ip_id) to prevent duplicate records at the database level. Migration 0002 canonicalizes existing rows and backfills fingerprints.
Value Format Enforcement Module | CredVault | Development | Yes | Completed | High | Data Validation | 2026-10-11 | 2026-10-11 | Created vault/validators.py module owning five format validators (URL, email, username, password, IP). Each provides is_valid_*, normalize_* (canonical spelling), and validate_* (raises ValidationError). Enforces strict RFC-compliant formats with normalization (e.g., HTTPS://Example.COM:443 → https://example.com).
Duplicate Prevention System | CredVault | Development | Yes | Completed | High | Data Validation | 2026-10-11 | 2026-10-11 | Three-layer duplicate prevention: (1) canonicalize before lookup, (2) unique=True on each reference name, (3) unique Account.fingerprint. Ensures Person@Example.COM and person@example.com resolve to one row. Import throughput maintained at 9,500+ rows/s.
Line Parser with Field Order Enforcement | CredVault | Development | Yes | Completed | Medium | Data Validation | 2026-10-11 | 2026-10-11 | Implemented vault/utils.py parse_line enforcing documented field order (URL → email-or-username → password → IP). Tries each separator (¦, tab, ;, :) and keeps first valid parse. Reads IP from end to handle separators inside passwords. Rejects invalid lines rather than storing half-parsed data.
Administrator Authentication | CredVault | Development | Yes | Completed | High | Authentication & Access Control | 2026-10-11 | 2026-10-11 | Implemented administrator login using Django's auth_user tables. Workspace requires authenticated administrator for all operations. Integrated with Django's authentication middleware and session management.
PostgreSQL Migration | CredVault | Development | Yes | Completed | High | Database Migration | 2026-10-11 | 2026-10-11 | Migrated from SQLite to PostgreSQL 14+. Implemented COPY-based import for high throughput, pg_trgm extension for substring search indexes, two-step paging for broad searches. Created copy_from_sqlite management command for migrating existing data with row count and fingerprint verification.
Trigram Index Implementation | CredVault | Development | Yes | Completed | Medium | Database Migration | 2026-10-11 | 2026-10-11 | Migration 0003 added pg_trgm GIN indexes on all reference tables for substring search. Reduced advanced keyword search from 1,156ms (SQLite) to 191ms (PostgreSQL). Import speed reduced by ~33% due to index maintenance (3,670 → 2,440 records/s on 200k test).
Bulk File & Folder Import | CredVault | Development | Yes | Completed | High | Import Engine | 2026-10-11 | 2026-10-11 | Implemented high-throughput bulk import in vault/importer.py. Streams input in bounded batches, bulk-creates deduplicated reference values, checks existing Account rows only for batch's URL/password subset. Supports single-file upload, full-folder upload (webkitdirectory), and local/server paths via web UI and importfolder management command.
Streaming CSV/JSON Export | CredVault | Development | Yes | Completed | Medium | Import Engine | 2026-10-11 | 2026-10-11 | Implemented StreamingHttpResponse with .values_list(...).iterator(chunk_size=2000) to stream entire matching dataset from database (not just current page). Supports CSV and JSON formats for full filtered result sets.
Parse Workers & Batch Optimization | CredVault | Development | Yes | Completed | High | Import Engine | 2026-10-11 | 2026-10-12 | Implemented parallel parse workers (default: min(4, CPU count)) to overlap parsing with database batches. Increased default batch size from 100k to 250k rows. Added --fast mode to drop trigram indexes during import and rebuild once at end. Achieved 7,700 records/s (22% improvement over baseline 5,900 records/s).
Import Performance Tuning & Documentation | CredVault | Documentation | Yes | Completed | Medium | Import Engine | 2026-10-11 | 2026-10-12 | Comprehensive performance documentation in README: postgresql.conf tuning (shared_buffers, work_mem, maintenance_work_mem), environment variables (VAULT_IMPORT_WORKERS, VAULT_IMPORT_BATCH_ROWS, VAULT_MAINTENANCE_WORK_MEM), batch size recommendations, and measurement commands. Documented that GPU does not help (CPU/disk-bound workload).
Query-Only Display & Indexed Search | CredVault | Development | Yes | Completed | High | Search & Query | 2026-10-11 | 2026-10-11 | Prevents dumping unqueried records across millions of rows. Records only queried and displayed when user searches. Supports instant (<1s) B-tree indexed lookups by domain, URL, email, username, password, or IP address. Domain search also matches paths under domain using B-tree range scans.
Advanced Substring Search | CredVault | Development | Yes | Completed | Medium | Search & Query | 2026-10-11 | 2026-10-11 | Implemented substring (contains) matching on Advanced search using pg_trgm GIN indexes. Settled on substring semantics (not prefix or full-text ranking) to match user expectations. Substring search over 1M records: ~200ms. Quick search stays exact for fast, predictable lookups.
Collation-Independent Domain Search | CredVault | Development | Yes | Completed | High | Search & Query | 2026-10-12 | 2026-10-13 | Migration 0006 added vault_url_name_lower_c_idx on lower(name) COLLATE "C" for byte-order comparisons. Fixed Windows locale collation issue where U+FFFF upper bound didn't reliably sort above ordinary text. Range scans now use COLLATE "C" with U+10FFFF bound, making domain search work identically across all database collations.
Profile Menu UI | CredVault | Development | Yes | Completed | Medium | UI/UX & Frontend | 2026-10-11 | 2026-10-11 | Replaced sidebar account block with profile button opening popover. Includes account details, quick actions, language selector, theme controls, and logout. Updated navigation in base.html template.
Browser Verification & Mobile Layout | CredVault | Testing | Yes | Completed | Medium | UI/UX & Frontend | 2026-10-11 | 2026-10-11 | Drove workspace in headless Chromium 153 through puppeteer-core against real app on PostgreSQL 16. Verified profile menu functionality and mobile layout responsiveness. Fixed layout issues discovered during browser testing.
Localization - Arabic RTL Support | CredVault | Development | Yes | Completed | Low | UI/UX & Frontend | 2026-10-11 | 2026-10-11 | Updated Arabic (ar) RTL translations using Django's translation framework. Compiled django.mo files. Language selector applies choice across workspace pages and remembers for session. Added translations for new validator strings and UI elements.
Durable Import Lifecycle Design | CredVault | Development | Yes | Completed | High | Import Reliability & Recovery | 2026-10-12 | 2026-10-12 | Designed state machine (pending → processing → completed/paused/interrupted). Created three new models: ImportJob (persistent import record with counters, worker lease, recovery state), ImportRecord (ledger entry per source record with status and account linkage), ImportRecoveryLog (audit trail). Migration 0005 creates tables with zero downtime.
Import Checkpointing & Atomic Batches | CredVault | Development | Yes | Completed | High | Import Reliability & Recovery | 2026-10-12 | 2026-10-12 | Implemented DurableImportSession wrapping BulkImportSession with persistent job tracking. Each batch committed atomically with synchronous_commit=ON. Ledger entries written in same transaction as accounts. Idempotent retries using deterministic keys (SHA-256 of job_id:position). Lease-based concurrency control with expiration.
Import Recovery & Resume Logic | CredVault | Development | Yes | Completed | High | Import Reliability & Recovery | 2026-10-12 | 2026-10-12 | Implemented discover_interrupted_jobs() to find abandoned jobs, recover_job() to reconcile ledger with database state and recalculate counters from authoritative ledger. Resume from earliest unaccounted work using PositionedLine to preserve original source positions. Recovery can actually resume imports with lines_factory_for_job().
Import Management Interface | CredVault | Development | Yes | Completed | Medium | Import Reliability & Recovery | 2026-10-12 | 2026-10-12 | Created import job list view (/import/jobs/), detail view with counters and recent failures, record-level ledger view with filtering. Added resume/cancel/pause/verify actions. Implemented sortable column headers with keyboard navigation and accessibility (aria-sort, role, tabindex). Five new templates for import management.
Import Reliability Verification & Defect Repair | CredVault | Development | Yes | Completed | High | Import Reliability & Recovery | 2026-10-12 | 2026-10-12 | Independent verification revealed 6 critical defects: (1) durable engine not integrated, (2) transaction durability compromised, (3) incorrect deduplication detection, (4) no account linkage in ledger, (5) recovery cannot resume, (6) skipped records not atomic. All fixed: integrated durable engine into web/CLI, removed synchronous_commit=off, used RETURNING clause for accurate dedup, added account_id linkage, implemented actual resume logic, wrapped skipped records in transaction.
Import Reliability Repair & Regression Fix | CredVault | Development | Yes | Completed | High | Import Reliability & Recovery | 2026-10-12 | 2026-10-13 | Fixed recovery counter persistence (counters now saved before state transition). Corrected FK handling in reconciliation tests (test-isolated simulation). Implemented Windows spawn parsing with _parse_context() fallback. Made domain search collation-independent. Fixed multi-file upload ledger position collisions (single session across files). All 155 tests passing, 39 import reliability tests passing.
Comprehensive Test Suite | CredVault | Testing | Yes | Completed | High | Testing & Verification | 2026-10-11 | 2026-10-13 | 155 tests in vault test suite covering: schema normalization, format validation, deduplication, authentication, PostgreSQL migration, import/export, search (exact and substring), import reliability (39 tests), crash recovery, lease management, idempotency, counter consistency. 2 intentional skips for opt-in performance measurements. All tests passing on Linux/PostgreSQL 18.6.
REMAINING TASKS
Background Worker Implementation | CredVault | Development | Yes | Not Started | High | Import Engine | 2026-10-20 | 2026-10-30 | Implement Celery or Dramatiq for asynchronous import processing. Current synchronous imports block web server for large files. Background workers will enable true async processing, better resource management, and proper interruption handling. Integrate with durable import engine for job tracking.
WebSocket/SSE Real-Time Progress | CredVault | Development | Yes | Not Started | Medium | Import Reliability & Recovery | 2026-10-25 | 2026-11-05 | Replace manual refresh import management UI with WebSocket or Server-Sent Events for real-time progress updates. Stream job status, stage, progress bar, and counter changes as they happen. Integrate with background worker for live updates during async imports.
Streaming Import Path Durability | CredVault | Development | Yes | Not Started | Medium | Import Reliability & Recovery | 2026-11-01 | 2026-11-10 | Migrate XHR-based streaming progress path (_stream_import_progress) from legacy BulkImportSession to durable engine. Currently provides no ImportJob records, no ledger entries, no durability guarantees. Requires background worker + WebSocket/SSE for proper async implementation. Deprecate synchronous streaming path.
Production Deployment & Verification | CredVault | Deployment | Yes | Not Started | High | Deployment & Operations | 2026-11-05 | 2026-11-10 | Deploy to production PostgreSQL environment. Run migration vault (additive, zero downtime). Execute full test suite (python manage.py test vault). Test import scenarios (small <100, medium 1k-10k, large 100k+). Test interruption and recovery. Verify import management UI. Monitor for issues. Validate performance metrics match documented benchmarks.
Windows Platform Verification | CredVault | Testing | Yes | Not Started | High | Testing & Verification | 2026-11-06 | 2026-11-08 | Re-run full test suite on Windows machine with locale-collated PostgreSQL cluster. Verify spawn-based workers work correctly. Confirm collation-independent domain search fixes. Test frozen executable with multiprocessing.freeze_support(). Measure spawn throughput vs fork on large imports. All fixes are platform-independent by construction but need native confirmation.
Large-Import Throughput Benchmarking | CredVault | Testing | Yes | Not Started | Medium | Testing & Verification | 2026-11-08 | 2026-11-12 | Run opt-in throughput tests (ImportThroughputTests) with hundreds of thousands to millions of rows. Benchmark durable engine with per-batch Python fingerprint/ledger lookups. Measure vault_url_name_lower_c_idx write cost. Test fast-mode interaction with index drop/rebuild. Validate performance on production hardware. Document actual vs expected throughput.
Real Crash Recovery Testing | CredVault | Testing | Yes | Not Started | High | Testing & Verification | 2026-11-10 | 2026-11-13 | Execute true SIGKILL/TerminateProcess tests of runserver/importfolder workers against live cluster. Verify WAL recovery and synchronous_commit behavior at OS level. Test power-loss scenarios. Validate crash recovery with subprocess-based tests. Ensure no data loss or corruption under real-world failure conditions. Document limitations and durability guarantees.
Source File Versioning & Management | CredVault | Development | Yes | Not Started | Low | Import Reliability & Recovery | 2026-11-12 | 2026-11-15 | Handle source file changes between import and resume. Currently recovery requires source file to exist unchanged on same machine. Options: store source file content (small files), require re-upload on resume, implement source file versioning, or add source hash revalidation per line. Uploaded files cannot auto-resume (content not kept on disk).